## Sheet1
Issue | Transaction Detail | Application | Issue Description | Owner | Comments | Resolution | Status | Comments
1 | Batch #: 20210329.000071 | XML and Txt Output | Date Format should be mm/dd/yyyy, total in header | Nick Pangori/Nathan Moreton | 3/31 - Date format completed. Total in header is wrong because the Action Center user failed to verify this amount, so that is not an issue with the script. We're adding a validation after export to handle this and the other required fields | Made change to export logic. Adding validation logic post export | Ready to Test
2 | Batch #: 20210329.000072 | XML and Txt Output | Invoice date format should be mm/dd/yyyy | Nathan Moreton | 3/31 - Completed | Made change to export logic | Ready to Test
3 | Batch #: 20210329.000073 | XML and Txt Output | Invoice date is blank | Nick Pangori/Nathan Moreton | 4/1 - Completed | Made invoice date a required field. Export validation will validate that all of the below fields are populated: vendor, BU, invoice date, invoice #, qty, part #, and price | Ready to test
4 | Batch #: 20210329.000074 | XML Output | Tax is 000, should be 0.00, date should have a 4 digit year format | Nick Pangori/Nathan Moreton | 3/31 - Date format completed. The amount field was entered manually in the incorrect way |  | Ready to Test
5 | Batch #: 20210329.000074 | TXT Output | Date Format should be mm/dd/yyyy and Total Format, tax is 000, should be 0.00 | Nick Pangori/Nathan Moreton | 3/31 - Date format completed 4/1 - Tax format completed | Made change to export logic | Ready to Test
6 |  | Document Understanding | UiPath digitization error due to VM memory | Nathan Moreton/Zach Coles | 3/31 - Added additional detail to log files for review. Processed staged invoices from Liz 4/1 - Still receiving issues. Ashling reviewing the log files and will escalate to UiPath. Tried suggestion of editing config csv | Added memory to the VM. Will continue to monitor during IT and performance testing | Ready to Test
7 |  | Document Understanding | No longer have a need for the copy of the file from the Input/region folder to the Processed/region folder | Dann Deaver | 4/1 - This is required to help the bot determine what invoices have been processed vs not. We recommend leaving as is and purging the folder | When invoice is processed delete it rather than move to processed folder | Nathan / Nick to merge into script
8 |  | Document Understanding | Non-PO special/service invoices. These will export with the image file and should be allowed to go through without a PO. | Nathan Moreton | 4/1 - Code exists. Require further testing 4/2 - There's not currently a field in action center for the Vendor number. Need to add this. | Non-PO invoices treated as normal until point of export | In Progress
9 |  | Document Understanding | APAC files not being processed | Dann Deaver | 3/31 - Trying to find a way to read the massive log file generated by this run. This is most likely being caused by the file names being too long 4/1 - Several of the APAC files failed because they were not invoices but random files like passport scans and terms of service. We were running into validation issues with several of the ones that were actually invoices, and all of these issues have been resolved. We still need to do the file name length dev. 4/2 - As the file names are shortened, the first 6 fields (underscore delimited) need to be kept. Will check with Dan to determine what happens if there is not an underscore. | RPA - Use regex to cut the file names to shorter amount to allow for ingestion. Testing will be neede to determine length. | Nathan / Nick to merge into script
10 |  | Action Center | Add region to the title label within Action Center. Allow for filtering of actions based on filter | Dann Deaver | 4/1 - Ashling working on adding this logic. Target readiness would be 4/2 4/2 - As the file names are shortened, the first 6 fields (underscore delimited) need to be kept. Will check with Dan to determine what happens if there is not an underscore. | Pass value from import folder. Region code added to file name as prefix | In Progress
11 | File Name: Test 8 in the AP folder | Document Understanding | Classification activity returns null value | Nick Pangori | 4/1 - null value was being returned because the word "Invoice" was not present in the pdf. The ML model now works for pdfs that don't contain the word "Invoice" 4/2 - This should be allowed to process any files, we shouldn't need a check for any words in the file. | Changed the learningfile.json to read invoices with the words "invoice." "plexus," or "a" so that all are processed | Ready to Test
12 |  | Document Understanding | Exception handling folders. Can we have one folder for invoice exceptions (invoice # and invoice date populated) vs other exceptions? | Nathan Moreton |  |  | In Progress
| FileName: 20210402.000099.txt | ACTION Center TXT Output XML | TXT: No line item number in the ECMDetail line. This is a requirement and it shouldn't have passed. Action Center: When in Action Center, this was # 450 and I was not allowed to update the line item. XML: Currency not specified, PDF name is not updated in the page field, it still has the old name. |  |  |  | NEW
| FileName:10210402.000100.xml | txt xml | XML: Page number should be same as the xml batch number, not the original file name. TXT: ECMDTL line, the total was typed in as on the screen with a "," instead of a decimal and was not converted over on the txt file. (this was updated in Action Center with a ,. |  |  |  | NEW
|  | ACTION Center | one of the files from NA did not make it to Action Center, why? |  |  |  | NEW
|  | ACTION Center | The way action center processes the data will not work, this is what it did: - Processed APAC (3 files), waited for me to complete in Action Center - Processed NA (2 of 3 files), waited for me to complete in Action Center - Processed RO (3 files), waited for me to complete in Action Center - Processed UK (3 files), waited for me to completed in Aciton Center - Reprocessed files that did not pass, waited for me to complete in Action Center - Processed CN, waited for me to complete in Action Center |  |  |  | NEW
| Action Center #461, 462, 463 | ACTION Center | PDF came in blank. Data is extracted, but I cannot see anything on the invoices. |  |  |  | NEW